## Sheet1
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Finalizing the project topic
Project proposal presentation submission
Literature review about vortex induced vibration and VIVACE converter models
Literature review about non linear vibrations
Literature review about power take-off systems
Understaning of existing mathematical models
Mid Video Presentation and viva
Develop a mathematical model for VIVACE
Design and simulation of the scaled-lab prototype
Demostration
Lab prototype fabrication (without generator)
Lab. Testing I
Implementation of the generator
Study possible improvements to the system
Lab. Testing II
Final Evaluations